|  |  |  |  |
| --- | --- | --- | --- |
| **Area/Goals** | **Action Plans** | **Person(s) Responsible** | **Timeline/Notes** |
| **Student Achievement/Curriculum**\*Adopt a new K-5 math curriculum  | \*Analyze, evaluate, and research current curriculum and new curriculum options\*Collaborate with junior high staff regarding current curriculum and new curriculum options \*Collaborate with and visit other K-5 schools regarding math curriculum\*Provide professional development that supports staff with implementation of curriculum | \*Principal\*Curriculum Coordinator\*K-5 Staff\*RtI Staff\*Junior High Math Teachers and Paraprofessionals\*Board of Education | \*Continue analysis, evaluation and research with completion goal by the end of the 2025-2026 school year\*Implement new curriculum for the 2026-2027 school year |
| **Finance** •Be a fiscally responsible school district that supports district operations, maintains financial stability, and is forward-thinking  | •Ongoing monitoring, projecting, forecasting, and planning, and continuation of monthly and yearly reports | \*Administration \*Bookkeeper\*Finance Committee\*Board of Education | \*Ongoing |
| **Facilities** \*Complete Solar Energy and Track Repair Projects\*Begin Phased Replacement Plan Grounded RTU Units in the 2004 Addition (4 of the 5 units need to be replaced)\*Monitor condition of Playground Equipment and explore creation of phased replacement plan in the future |  \*Launch and monitor Solar Energy Project\*Launch and monitor Track Repair Project\*Building and Grounds Committee meetings for planning\*Schedule follow up Playground Equipment inspection (Summer of 2026) | \*Administration\*Director of Facilities\*Building and Grounds Committee\*Board of Education\*Clean Energy Design Group | \*Solar Energy Project completion goal is the summer of 2025\*Track Repair Project completion goal is the summer of 2025\*Phased Replacement Plan for Grounded RTU’s – begin in 2025-2026 (FY26) with completion goal of Summer 2031 (FY31)\*No timetable for phased playground equipment plan (TBD – possibly 4-10 year timeframe) |
| **District/Community Relations** •Maintain and strengthen our unwavering commitment to transparency, engagement, and involvement for and with all stakeholders | •Implement and promote multi-faceted communication philosophy and approach   | \*Administration\*All Staff\*Board of Education | •Non-stop commitment is continually promoted and modeled\*New live-streaming service was implemented in Spring of 2024 |

Updated 6/23/25