|  |  |  |  |
| --- | --- | --- | --- |
| **Area/Goals** | **Action Plans** | **Person(s) Responsible** | **Timeline/Notes** |
| **Student Achievement/Curriculum**  \*Adopt a new K-5 math curriculum | \*Analyze, evaluate, and research current curriculum and new curriculum options  \*Collaborate with junior high staff regarding current curriculum and new curriculum options  \*Collaborate with and visit other K-5 schools regarding math curriculum  \*Provide professional development that supports staff with implementation of curriculum | \*Principal  \*Curriculum Coordinator  \*K-5 Staff  \*RtI Staff  \*Junior High Math Teachers and Paraprofessionals  \*Board of Education | \*Continue analysis, evaluation and research with completion goal by the end of the 2025-2026 school year  \*Implement new curriculum for the 2026-2027 school year |
| **Finance**  •Be a fiscally responsible school district that supports district operations, maintains financial stability, and is forward-thinking | •Ongoing monitoring, projecting, forecasting, and planning, and continuation of monthly and yearly reports | \*Administration  \*Bookkeeper  \*Finance Committee  \*Board of Education | \*Ongoing |
| **Facilities**  \*Complete Solar Energy and Track Repair Projects  \*Begin Phased Replacement Plan Grounded RTU Units in the 2004 Addition (4 of the 5 units need to be replaced)  \*Monitor condition of Playground Equipment and explore creation of phased replacement plan in the future | \*Launch and monitor Solar Energy Project  \*Launch and monitor Track Repair Project  \*Building and Grounds Committee meetings for planning  \*Schedule follow up Playground Equipment inspection (Summer of 2026) | \*Administration  \*Director of Facilities  \*Building and Grounds Committee  \*Board of Education  \*Clean Energy Design Group | \*Solar Energy Project completion goal is the summer of 2025  \*Track Repair Project completion goal is the summer of 2025  \*Phased Replacement Plan for Grounded RTU’s – begin in 2025-2026 (FY26) with completion goal of Summer 2031 (FY31)  \*No timetable for phased playground equipment plan (TBD – possibly 4-10 year timeframe) |
| **District/Community Relations**  •Maintain and strengthen our unwavering commitment to transparency, engagement, and involvement for and with all stakeholders | •Implement and promote multi-faceted communication philosophy and approach | \*Administration  \*All Staff  \*Board of Education | •Non-stop commitment is continually promoted and modeled  \*New live-streaming service was implemented in Spring of 2024 |

Updated 6/23/25